## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | MPD-US-01 | Understand requirements for sales call audio capture | MUST HAVE | — | Mitali Pawan Doble | 1- Not Started
1 | 1 | MPD-US-01 | Design architecture for live & uploaded audio | MUST HAVE | — | Mitali Pawan Doble | 2- In Progress
1 | 1 | MPD-US-01 | Implement audio upload module | MUST HAVE | — | Mitali Pawan Doble | 2- In Progress
1 | 1 | MPD-US-01 | Implement live audio recording feature | MUST HAVE | — | Mitali Pawan Doble | 3- Completed
1 | 1 | MPD-US-02 | Research Whisper speech-to-text model | MUST HAVE | Sprint 1 | Mitali Pawan Doble | 3- Completed
1 | 1 | MPD-US-02 | Integrate Whisper for recorded audio | MUST HAVE | Sprint 1 | Mitali Pawan Doble | 2- In Progress
1 | 1 | MPD-US-02 | Integrate Whisper for live audio | MUST HAVE | Sprint 1 | Mitali Pawan Doble | 2- In Progress
1 | 1 | MPD-US-02 | Validate transcription accuracy | MUST HAVE | Sprint 1 | Mitali Pawan Doble | 3- Completed
1 | 1 | MPD-US-03 | Design transcript storage with timestamps | MUST HAVE |  | Mitali Pawan Doble | 1- Not Started
1 | 1 | MPD-US-03 | Store transcript data | MUST HAVE |  | Mitali Pawan Doble | 2- In Progress
1 | 1 | MPD-US-03 | Validate transcript persistence | MUST HAVE |  | Mitali Pawan Doble | 3- Completed
2 | 2 | MPD-US-04 | Study sentiment analysis techniques | MUST HAVE | Sprint 1 | Mitali Pawan Doble | 1- Not Started
2 | 2 | MPD-US-04 | Implement sentiment analysis module | MUST HAVE | Sprint 1 | Mitali Pawan Doble | 2- In Progress
2 | 2 | MPD-US-04 | Test sentiment scoring | MUST HAVE | Sprint 1 | Mitali Pawan Doble | 3- Completed
2 | 2 | MPD-US-05 | Define customer intent categories | MUST HAVE | Sprint 1 | Mitali Pawan Doble | 1- Not Started
2 | 2 | MPD-US-05 | Implement intent detection logic | MUST HAVE | Sprint 1 | Mitali Pawan Doble | 2- In Progress
2 | 2 | MPD-US-05 | Validate intent classification | MUST HAVE | Sprint 1 | Mitali Pawan Doble | 3- Completed
2 | 2 | MPD-US-06 | Study entity extraction (NER) | MUST HAVE | Sprint 1 | Mitali Pawan Doble | 1- Not Started
2 | 2 | MPD-US-06 | Extract product, price, features | MUST HAVE | Sprint 1 | Mitali Pawan Doble | 2- In Progress
2 | 2 | MPD-US-06 | Validate extracted entities | MUST HAVE | Sprint 1 | Mitali Pawan Doble | 3- Completed
3 | 3 | MPD-US-08 | Research speaker diarization | SHOULD HAVE | Sprint 2 | Mitali Pawan Doble | 1- Not Started
3 | 3 | MPD-US-08 | Separate customer & salesperson speech | SHOULD HAVE | Sprint 2 | Mitali Pawan Doble | 2- In Progress
3 | 3 | MPD-US-08 | Validate speaker identification | SHOULD HAVE | Sprint 2 | Mitali Pawan Doble | 3- Completed
3 | 3 | MPD-US-10 | Setup Ollama Phi model | MUST HAVE | Sprint 2 | Mitali Pawan Doble | 1- Not Started
3 | 3 | MPD-US-10 | Prompt design for AI reasoning | MUST HAVE | Sprint 2 | Mitali Pawan Doble | 2- In Progress
3 | 3 | MPD-US-10 | Test AI reasoning outputs | MUST HAVE | Sprint 2 | Mitali Pawan Doble | 3- Completed
4 | 4 | MPD-US-11 | Design AI-based next question logic | MUST HAVE | Sprint 3 | Mitali Pawan Doble | 1- Not Started
4 | 4 | MPD-US-11 | Generate next-question suggestions | MUST HAVE | Sprint 3 | Mitali Pawan Doble | 2- In Progress
4 | 4 | MPD-US-11 | Validate next-question relevance | MUST HAVE | Sprint 3 | Mitali Pawan Doble | 3- Completed
4 | 4 | MPD-US-12 | Implement objection handling logic | SHOULD HAVE | Sprint 3 | Mitali Pawan Doble | 2- In Progress
4 | 4 | MPD-US-12 | Test objection handling responses | SHOULD HAVE | Sprint 3 | Mitali Pawan Doble | 3- Completed
4 | 4 | MPD-US-13 | Implement product recommendation | MUST HAVE | Sprint 3 | Mitali Pawan Doble | 2- In Progress
4 | 4 | MPD-US-13 | Validate product recommendations | MUST HAVE | Sprint 3 | Mitali Pawan Doble | 3- Completed
4 | 4 | MPD-US-15 | Final UI testing & project closure | COULD HAVE | Sprint 4 | Mitali Pawan Doble | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7