## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Mitali Pawan Dobale | 2025-10-18 | Uploaded audio not converting to text correctly for noisy samples | Sprint 1 | Developer | Logical | Audio preprocessing improved (noise reduction + resampling) | 2025-10-18 | Closed | Issue resolved after standardizing audio format
2 | Mitali Pawan Dobale | 2025-11-03 | Sentiment analysis giving incorrect result for neutral customer responses | Sprint 1 | Developer | Logical | Updated sentiment model threshold and tested with mock calls | 2025-11-03 | Closed | Accuracy improved
3 | Mitali Pawan Dobale | 2025-11-08 | Speaker diarization not separating customer and salesperson clearly | Sprint 2 | Developer | Logical | Improved diarization logic using timestamp-based speaker tagging | 2025-11-08 | Closed | Speaker labels now consistent
4 | Mitali Pawan Dobale | 2025-11-12 | Entity extraction missing product names in some transcripts | Sprint 2 | Developer | Maintainability | Updated NER pipeline and prompt structure | 2025-11-12 | Closed | Entity recall increased
5 | Mitali Pawan Dobale | 2025-11-20 | Ollama (phi3:mini) not generating AI suggestions for some inputs | Sprint 2 | Developer | Logical | Prompt refined and JSON-safe parsing added | 2025-11-20 | Closed | Stable AI response generation
6 | Mitali Pawan Dobale | 2025-11-25 | Live audio recording not starting on some browsers | Sprint 3 | Developer | User Interface Standards | Added microphone permission handling and UI warning | 2025-11-25 | Closed | Works across Chrome/Edge
7 | Mitali Pawan Dobale | 2025-11-28 | UI layout cluttered when displaying transcript and AI suggestions together | Sprint 3 | Developer | User Interface Standards | Redesigned UI using columns and cards | 2025-11-28 | Closed | Improved readability
8 | Mitali Pawan Dobale | 2025-11-02 | AI next-question suggestions repeating similar questions | Sprint 3 | Developer | Logical | Added conversation history context to Ollama prompt | 2025-11-02 | Closed | Suggestions now diverse
9 | Mitali Pawan Dobale | 2025-12-06 | Product recommendation not matching customer budget | Sprint 4 | Developer | Logical | Included entity-based budget filtering in reasoning layer | 2025-12-06 | Closed | Recommendations more relevant
10 | Mitali Pawan Dobale | 2025-12-06 | Auto-reply generation too long for real-time use | Sprint 4 | Developer | Maintainability | Limited response length via prompt constraints | 2025-12-06 | Closed | Faster and concise replies
11 | Mitali Pawan Dobale | 2025-12-08 | Report download button not responding | Sprint 4 | Developer | User Interface Standards | Fixed file path and Streamlit callback issue | 2025-12-08 | Closed | PDF/CSV download working
12 | Mitali Pawan Dobale | 2025-12-09 | Application crashes when Ollama service is stopped | Sprint 4 | Developer | Logical | Added Ollama availability check and error handling | 2025-12-09 | Closed | Graceful error message shown

## Sheet2
Logical
User Interface
Maintainability
Standards
Others